## Job summary
Salem Housing Authority - 5 Barton Square Low-Slope Roof Replacement: Job summary
Historical records from the Salem Housing Authority January 10, 2024 board packet (original PDF pages 114-120). They describe conditions reported in December 2023, not the current condition of the roof.
Section | Field | Value | Source page | Other source page | Notes (interpretation marked)
Source | Source document | Salem Housing Authority, January 10, 2024 Board Packet (126 pages); this workbook uses original PDF pages 114-120 only | p.114 |  | Source URL: https://salemha.org/wp-content/uploads/2024/01/January-10-2024-Board-Packet.pdf. Page links open the original public PDF at the cited page.
Source | Record status | Historical observations (December 2023) |  |  | Interpretation/caveat: nothing in these pages records that punch-list work was later completed, inspected or accepted. Do not read this workbook as the job's current condition.
Project | Project | Low-Slope Roof Replacement | p.114 | p.115
Project | Location | 5 Barton Square, Salem, MA | p.114 | p.115 | G704 prints "5 Barton Square Salem MA" (no ZIP). Garland report lists Facility "Barton Sq" (p.117).
Project | Roof section (Garland report) | Main Roof Section | p.117
Project | Work certified substantially complete | The entire roof. | p.114
Organizations | Owner | Salem Housing Authority, 27 Charter Street, Salem, MA 01970 | p.114 |  | Address as printed on the G704. The Garland report header (p.117) prints a different address: "Salem Housing Authority, 16A Rainbow Terrace, Salem, Massachusetts 01970". Both are reproduced as printed; the source pages do not explain the variation.
Organizations | Owner signatory (named) | Cathy Hoog, Executive Director | p.114 |  | Owner signature and date lines are blank on this copy of the G704.
Organizations | Owner contacts copied | Debra Tucker, Salem Housing; Gary Dean, Salem Housing | p.116 |  | Listed as Cc on the Brockway punch list letter.
Organizations | Architect | Andrew M. Brockway & Associates, 209 Parker Street, Acton, MA 01720 | p.114 | p.115 | Letterhead also gives 978 793-1550 and www.brockwayarch.com (p.115).
Organizations | Architect signatory | Andrew M. Brockway, Principal (signed G704); Andrew M. Brockway, AIA (signed letter) | p.114 | p.116
Organizations | Contractor | W.P.I. Construction Inc., 5 Checkerberry Island, Webster, MA 01570 | p.114 |  | Address as printed on the G704. The Brockway letter (p.115) addresses W.P.I. Construction, Inc. at a different address: "4 Tanner Road, Webster, MA 01" (ZIP printed only as "01" on this copy). Both are reproduced as printed; the source pages do not explain the variation.
Organizations | Contractor signatory | Walter Piwowarczyk, President | p.114 | p.115 | Signed the G704; also the addressee of the punch list letter.
Organizations | Roofing field report source | Garland ("Garland Roofing"); Rob Verreault named | p.115 | p.117 | The Brockway letter says to "Refer to attached Field Report from Rob Verreault at Garland Roofing" (p.115); the G704 also cites a "Field Report from Garland Roofing". The Garland pages that follow (pp.117-120) are titled "Progress Report" and do not themselves name an author.
Dates | Contract date | 2023-10-18 | p.114 |  | G704 "Contract For:" field is blank on this copy.
Dates | Date of Substantial Completion | 2023-12-15 | p.114 |  | Stated by the architect on the G704 for "The entire roof."
Dates | Architect punch list date | 2023-12-15 | p.114 | p.115 | Printed as "12.15.23" (G704 and letter RE line).
Dates | Garland Progress Report date | 2023-12-19 | p.117 |  | Printed as "12/19/2023" (header and Report Date). The G704 dated 12.22.23 (p.114) describes the 12.15.23 punch list as "including Field Report from Garland Roofing", and the Dec 22, 2023 letter (p.115) refers to the attached Garland field report. The report date falls between the punch-list date and those Dec 22 documents. These Garland pages follow the letter in the packet and are treated as that attached report.
Dates | G704 certificate date | 2023-12-22 | p.114 |  | Printed as "12.22.23"; Certificate Number 001.
Dates | Brockway punch list letter date | 2023-12-22 | p.115
Dates | Contractor signature date (G704) | 2023-12-22 | p.114
Dates | Owner signature date (G704) | Blank on this copy | p.114
Completion | Certificate number | 1 | p.114 |  | Printed as "001".
Completion | Work to be completed or corrected | Punch List from Andrew M. Brockway & Associates dated 12.15.23 including Field Report from Garland Roofing | p.114 |  | See the Punch list sheet.
Completion | Time allowed for punch list | 21 (twenty-one) days from the date of Substantial Completion | p.114 |  | Calendar arithmetic (interpretation, not printed in source): 15 Dec 2023 + 21 days = 5 Jan 2024.
Completion | Warranty commencement | Date of Substantial Completion; for items on the attached list, the date of issuance of the final Certificate of Payment or the date of final payment, whichever occurs first | p.114 |  | The G704 exceptions field for warranties is blank.
Completion | Owner/Contractor responsibilities | Owner is responsible for above listed items (the form lists security, maintenance, heat, utilities, damage to the Work, insurance) | p.114
Amounts | Cost estimate of Work to be completed or corrected | 7500 | p.114 |  | The only monetary amount stated in these pages. No contract sum, payment or retainage amounts appear.

## Punch list
Punch list - reported issues (Brockway 12.15.23 punch list and Garland 12/19/2023 report)
Historical records from the Salem Housing Authority January 10, 2024 board packet (original PDF pages 114-120). They describe conditions reported in December 2023, not the current condition of the roof.
Item | Issue | Reported observation(s) (source wording) | Documented action | Location (as reported) | Brockway punch list 12.15.23 | Garland report 12/19/2023 | Associated photograph(s) (captions quoted; descriptions ours) | Photo page | Interpretation / unresolved (not from source)
PL-01 | Roof hatch closing latch missing | Brockway item 1: "The closing latch on the roof hatch is missing." Garland (2): "Latch or lock needed" | Brockway: "Purchase and replace the latch." (Garland caption states the need only.) | Roof hatch | Item 1 - p.115 | (2) - p.118 | p.115: SAMPLE roof hatch latch from Babcock-Davis, a reference image only; caption: "(I am not sure if the Salem hatch is the same)". It is not a photo of the Salem site. p.118: Garland photo (2); our description: a hatch-type lid viewed from below. | Garland photo (2) - p.118 | Interpretation: Brockway item 1 and Garland (2) are treated as the same roof-hatch latch condition; Garland's caption does not say "hatch" and the match rests on the photo. Unresolved: whether the Salem hatch takes the Babcock-Davis latch shown (the architect was unsure).
PL-02 | Damaged brick veneer at rounded corner near fascia | Brockway item 2: "The brick veneer near the fascia at the back of the building near the rounded corner has been damaged - presumably from the lull bringing materials to and from the roof." Garland (5): "Damaged brick" | Brockway: "Repair the brick veneer." (Garland caption gives no action.) | Back of the building, near the fascia, near the rounded corner | Item 2 - p.115 | (5) - p.119 | p.116: "Brick cornice before construction" and "Brick cornice after construction" (after photo has a red dashed box marking an area of the brick). p.119: Garland photo (5); our description: a rounded brick corner below the roof edge. | Before/after photos - p.116 | Cause is the architect's presumption ("presumably from the lull"), not an established fact. Interpretation: Garland (5) appears to show the same rounded corner as the p.116 after photo, so it is reconciled here. Text says "brick veneer" while photo captions say "brick cornice". No extent or quantity given.
PL-03 | Fish mouth at expansion joint | Garland (1): "Fish mouth at expansion joint." | Not specified in source. | Expansion joint, Main Roof Section (exact position not stated) | Not listed | (1) - p.117 | p.117: Garland photo (1); our description: membrane surface at a raised joint. | Garland photo (1) - p.117 | Included because Brockway refers roofing items to the Garland report. Repair method not documented.
PL-04 | Seams around drain - salvage sheet (Garland 3) | Garland (3): "6 x 2 salvage sheet over both seams around drain." | As captioned: "6 x 2 salvage sheet over both seams around drain." | Around a roof drain (which drain is not stated) | Not listed | (3) - p.118 | p.118: Garland photo (3); our description: a drain in the open roof field with a person walking nearby. | Garland photo (3) - p.118 | Kept separate from PL-05: the caption wording is identical but the photos appear to show different drains (interpretation). Units for "6 x 2" are not stated. "salvage" reproduced as printed (possibly meant "selvage"; not confirmed). The underlying seam condition is not described in words.
PL-05 | Seams around drain - salvage sheet (Garland 4) | Garland (4): "6 x 2 salvage sheet over both seams around drain." | As captioned: "6 x 2 salvage sheet over both seams around drain." | Around a roof drain (which drain is not stated) | Not listed | (4) - p.119 | p.119: Garland photo (4); our description: a drain near the roof edge, with an arched-window brick building at left. | Garland photo (4) - p.119 | Kept separate from PL-04 (see PL-04). Unresolved: if both photos show the same drain, PL-04 and PL-05 would be one item. Units for "6 x 2" are not stated.
PL-06 | End dam requires caulk | Garland (6): "End dam requires caulk. Opposite side of parapet." | Caulk the end dam (caption: "requires caulk"). | "Opposite side of parapet" (as printed) | Not listed | (6) - p.120 | p.120: Garland photo (6); our description: a parapet corner with a metal flashing piece at upper left. | Garland photo (6) - p.120 | Unresolved: "opposite side" is not tied to a reference point in the source.